## RFI
TDM RFI # | Miclex RFI # | Subject | Date | Response

## PCN
Date | PCN # | Subject | Subject | Affect TDM Scope | AD Folder Updated | Priced | Approved
2025-02-27 | Clarification 2445-01 | Project Manual/Structural |  | No | No
2025-03-17 | Clarification 2445-03 | Mechanical |  | No | No
2025-03-17 | PCN 2445-01 | Chainlink Fencing @ Refirgeration |  | No | No
2025-03-19 | PCN 2445-02 | Loading Ramp |  | No | No
2025-04-30 | PCN 2445-03 | CANCELLED
2025-04-04 | PCN 2445-04 | Electrical |  | No | No
2025-04-08 | PCN 2445-05 | Add Sidwalk |  | No | No
2025-04-08 | PCN 2445-06 | Add Wall & Handrailing |  | No | No
2025-04-09 | PCN 2445-07 | Maglocks |  | No | No
2025-04-15 | PCN 2445-08 | Add Door |  | No | No
2025-04-30 | PCN 2445-09 | Electrical |  | No | No
2025-04-24 | PCN 2445-10 | Electrical |  | No | No
2025-05-01 | PCN 2445-11 | Electrical |  | No | No
2025-05-02 | PCN 2445-11R1 | Electrical |  | No | No
2025-05-13 | PCN 2445-12 | Exterior Signage |  | No | No
2025-06-05 | PCN 2445-13 | Architectural |  | Yes | Yes | Yes
2025-05-12 | PCN 2445-14 | Electrical |  | No | No
2025-05-14 | PCN 2445-15 | Eliminate Mobile Floral |  | No | No
2025-05-28 | PCN 2445-16 | Mechanical |  | No | No
2025-06-05 | PCN 2445-18 | Architectural/Framing |  | No | No
2025-06-05 | PCN 2445-19 | Mechanical |  | No | No
2025-07-10 | PCN 2445-20 | Electrical |  | No | No
2025-07-10 | PCN 2445-21 | Electrical |  | No | No
2025-07-17 | PCN 2445-22 | Electrical |  | No | No
2025-07-17 | PCN 2445-23 | Exterior |  | No | No
2025-07-30 | PCN 2445-24 | Mechanical |  | No | No
2025-07-30 | PCN 2445-25 | Electrical |  | No | No
2025-07-30 | PCN 2445-26 | Electrical |  | No | No
2025-08-01 | PCN 2445-27 | Architectural |  | No | No
2025-08-01 | PCN 2445-28 | Architectural |  | Yes | Yes | Yes
2025-08-05 | PCN 2445-30 | Electrical |  | No | No
2025-08-13 | PCN 2445-31 | Electrical |  | Maybe? | No
2025-08-15 | PCN 2445-32 | Electrical |  | No | No
2025-08-20 | PCN 2445-33 | Mechanical |  | No | No
2025-08-20 | PCN 2445-34 | Architectural |  | No | No
2025-09-05 | PCN 2445-35 | Electrical/Fixturing |  | No | Yes
2025-09-09 | PCN 2445-36 | Electrical |  | No | No
2025-09-08 | PCN 2445-37 | Electrical |  | No | No
10-Ocober-25 | PCN 2445-39 | Electrical | 4 cold side and salad power | No | No
10-Ocober-25 | PCN 2445-40 | Architectural/Electrical/Mechanical | Janitor room smoke damper | No | No
15-Ocober-25 | PCN 2445-41 | Architectural/Structural | Rolling shuter HSS | No | No
19-Ocober-25 | PCN 2445-42 | Architectural | Floral glass shelves | Yes | Yes | Yes
23-Ocober-25 | PCN 2445-43 | Electrical | HMR Ref. Service Hot Power | No | No
28-Ocober-25 | PCN 2445-43R1 | Electrical | HMR Ref. Service Hot Power | No | No
20-Ocober-25 | PCN 2445-44 | Electrical/Fixturing | IDF Closet Power | No | No
2025-11-05 | PCN 2445-45 | Electrical | Power for Dry System Compressor | No | No
2025-11-06 | PCN 2445-46 | Architectural | Deli Bulkhead | No | No
2025-11-06 | PCN 2445-47 | Mechanical | Provide Domestic Cold Water Line to Misting Stations | No | No
2025-11-17 | PCN 2445-48 | Architectural | Delete Stainless Steel Railing @ Floral | Yes | Yes | Yes | Yes
2025-11-17 | PCN 2445-49 | Architectural | Delete floral glasse & posts | Yes | Yes
2025-11-25 | PCN 2445-51 | Electrical | Dry Misting System Power | No | No
2025-11-27 | PCN 2445-54 | Electrical | Frozen Foods Refrigeretion Defrost Heaters | No | No
2025-11-27 | PCN 2445-53 | Electrical | Checkout pop cooler power | No | No
2025-11-28 | PCN 2445-55 | Electrical | Illuminate depatment letters | No | No
2025-12-01 | PCN 2445-56 | Architectural/Electrical | Pharmacy Bulkhead | NO | Yes
2025-12-05 | CL 2445-15 | Architectural | Finishes of Pony Walls | Yes | Yes
2025-12-03 | PCN 2445-57 | Architectural | Grade Beam Covering | No | No
2025-12-23 | PCN 2445-58 | Electrical | Olive Bar Electrical | No | No
2025-12-23 | CL 2445-16 | Electrical | Lighting at RTU-1 | No | No
2025-12-23 | PCN 2445-59 | Electrical | Snack Bar Cooler (Propane | No | No
2025-12-23 | PCN 2445-60 | Electrical | Soup Island | No | No
2025-12-23 | PCN 2445-61 | Electrical | Bakery Spiral Mixer | No | No
2025-12-23 | PCN 2445-62 | Electrical | Bakery Sheeter | No | No
2026-01-06 | PCN 2445-63 | Electrical | Data Rack Receptacles – Room # 112 | No | No